## Simple version
| Start | End | Duration
Develop learning objectives | 2009-03-01 | 2009-03-13 | 13 | Activity
Develop Treatment | 2009-03-13 | 2009-03-28 | 16 | Activity
Treatment Signed-off | 2009-03-31 | 2009-03-31 | 0.9 | Milestone
Brief Agency | 2009-04-06 | 2009-04-09 | 4 | Activity
Develop Script | 2009-04-01 | 2009-04-30 | 30 | Activity
Review Script | 2009-05-01 | 2009-05-08 | 8 | Activity
Script Signed-off | 2009-05-29 | 2009-05-29 | 0.9 | Milestone
Put Script into Templates | 2009-06-01 | 2009-06-06 | 6 | Activity
Plan Filming/Asset Capture | 2009-06-01 | 2009-06-06 | 6 | Activity
Film/Capture Assets | 2009-06-07 | 2009-06-21 | 15 | Activity
Edit/Encode Assets | 2009-06-28 | 2009-07-12 | 15 | Activity
Amend Content | 2009-07-13 | 2009-07-31 | 19 | Activity
Conduct User Acceptance Testing (UAT) | 2009-08-01 | 2009-08-15 | 15 | Activity
Compile UAT Results | 2009-08-16 | 2009-08-21 | 6 | Activity
Amend Content Based on UAT | 2009-08-22 | 2009-08-31 | 10 | Activity
Conduct Acceptance Review | 2009-09-01 | 2009-09-08 | 8 | Activity
Amend Content Based on Review | 2009-09-09 | 2009-09-16 | 8 | Activity
Integrate with existing Programmes | 2009-09-17 | 2009-09-29 | 13 | Activity
Final Acceptance Signed-off | 2009-09-30 | 2009-09-30 | 0.9 | Milestone
Launch | 2009-10-05 | 2009-10-05 | 0.9 | Milestone
| 39873 | Start: earliest date axis Minimum
| 40091 | End: latest date axis Maximum
Data entry in green cells
Calculated data in orange cells
Chart is a "Stacked Bar Chart"
Series 1 is the "Start Date"
Series 2 is the "Duration"
Set major grid lines at 28 days
Set minor gridlines at 7 days
To customise the timeline in the Gantt Chart:
You need to put the “Earliest date Minimum value” from cell B23 into the Axis Minimum and “Latest date Maximum value” from cell B24 into the Axis Maximum…
In Excel 2003/2007, right-click over the horizontal axis dates and select “Format Axis”. In the Axis Scale tab put the B24 value as a Fixed Minimum and the B25 value as a Fixed Maximum. I usually add a few days on to the Max so the chart is a bit wider than the actual bars of data.
Formulas:
End = [Start]
Note on B4: Ian Seath: Data entry in green cells Calculated data in orange cells
Note on C26: Ian Seath: Used to determine max and min values on chart date axis. Delete these once you've set the max and min axis values.
Note on E4: Ian Seath: This column "forces" a Milestone to have a duration of 0.9 Day so that it will display on the chart
Note on F4: Ian Seath: This column determines if the data in Column A is a Milestone or an Activity

## Milestone version
Project: Create e-learning course
| Start | End | Duration | Milestones
Develop learning objectives | 2009-03-01 | 2009-03-13 | 13 |  | Activity
Develop Treatment | 2009-03-13 | 2009-03-28 | 16 |  | Activity
Treatment Signed-off (M) | 2009-03-31 | 2009-03-31 | 0 | 1 | Milestone
Brief Agency | 2009-04-06 | 2009-04-09 | 4 |  | Activity
Develop Script | 2009-04-01 | 2009-04-30 | 30 |  | Activity
Review Script | 2009-05-01 | 2009-05-08 | 8 |  | Activity
Script Signed-off (M) | 2009-05-29 | 2009-05-29 | 0 | 1 | Milestone
Put Script into Templates | 2009-06-01 | 2009-06-06 | 6 |  | Activity
Plan Filming/Asset Capture | 2009-06-01 | 2009-06-06 | 6 |  | Activity
Film/Capture Assets | 2009-06-07 | 2009-06-21 | 15 |  | Activity
Edit/Encode Assets | 2009-06-28 | 2009-07-12 | 15 |  | Activity
Amend Content | 2009-07-13 | 2009-07-31 | 19 |  | Activity
Conduct User Acceptance Testing (UAT) | 2009-08-01 | 2009-08-15 | 15 |  | Activity
Compile UAT Results | 2009-08-16 | 2009-08-21 | 6 |  | Activity
Amend Content Based on UAT | 2009-08-22 | 2009-08-31 | 10 |  | Activity
Conduct Acceptance Review | 2009-09-01 | 2009-09-08 | 8 |  | Activity
Amend Content Based on Review | 2009-09-09 | 2009-09-16 | 8 |  | Activity
Integrate with existing Programmes | 2009-09-17 | 2009-09-29 | 13 |  | Activity
Final Acceptance Signed-off (M) | 2009-09-30 | 2009-09-30 | 0 | 1 | Milestone
Launch (M) | 2009-10-05 | 2009-10-05 | 0 | 1 | Milestone
|  |  | Activities | Milestones
| 39873 | Start: earliest date axis Minimum
| 40091 | End: latest date axis Maximum
Data entry in green cells
Calculated data in orange cells
Chart is a "Stacked Bar Chart"
Series 1 is the "Start Date"
Series 2 is the "Duration"
Series 3 is the "Milestones"
Chart Legend uses D23 and E23 for labels
Set major grid lines at 28 days
Set minor gridlines at 7 days
Formulas:
End = [Start]