SAMPLE Production Schedule (Narrative Format)

This is a sample production schedule showing the dates and periods for each major stage of production.

This has been done in a narrative format, but could also be done in a calendar format.

|  | Stage |  |  | From |  |  | To (times ) |  |  | Period |  | Notes |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Pre-production |  |  | Monday 5 January |  |  | Friday 23 January |  |  | 2 weeks |  |  |  |
|  | Location recce |  | Tuesday 13 January |  |  | 0830 – 1230 |  |  |  | 4 hours |  | All key crew booked |  |
|  | Shoot |  |  | Monday 19 January |  |  | Friday 23 January |  |  | 5 days |  |  |  |
|  | Edit |  |  | Monday 19 January |  |  | Friday 6 February |  |  | 3 weeks |  | Edit asst. required nights during shoot week |  |
|  | Rough cut screening |  | Monday 2 February |  |  |  |  |  | – |  |  |  |  |
|  | Investors’ screening |  | Wednesday 4 February |  |  |  |  |  | – |  |  |  |  |
|  | Compile |  |  | Friday 6 February |  |  |  |  |  | 6–8 hours |  | Edit asst. required night Thur 5 & all day Fri 6 |  |
|  | Grade |  |  | Tuesday 10 February |  |  | 0900 – 1400 |  |  | 4–5 hours |  | booked |  |
|  | Online |  |  | Tuesday 10 February |  |  | 1600 – 2000 |  |  | 3–4 hours |  | booked |  |
|  | Master tech check |  | Thursday 12 February |  |  |  | tbc |  |  | 2 hours |  | to be confirmed |  |
|  | Tracklay/foley |  | Saturday 7 February |  |  | Tuesday 10 February |  |  | 4 days |  |  | booked |  |
|  | Mix |  |  | Wednesday 11 February |  | 0900 – 1700 |  |  | 8 hours |  |  | booked |  |
|  | Dubs/tech checks |  | Thursday 12 February |  |  |  |  |  |  |  |  | Facility yet to be confirmed & booked |  |

Master/delivery	Friday 13 February	PA to assist with deliverable