## Lessons Learned
Lessons Learned from <Project Name>
Topic | Experience | Impact & Recurrence (H/M/L for each) | Rank | Lessons Learned | Best Practice or Problem? | Actions Required To Implement Lessons Learned | Implement (Q/S/L) | Assigned To

## Instructions
Instructional Notes for the Lessons Learned Template:
The Lessons Learned template represents a method for gathering Lessons Learned and then evaluating them to determine which ones are most important to address first. You can pre-poluate the template with Categories and ask team members to populate the “Experience” and “Lessons Learned” sections prior to the meeting. The following descriptions of each column heading provide an example of what should be populated in each of the columns:
Topic: | Brief description (5 – 7 words) of the topic to be discussed
Experience: | Several sentences describing the situation and what the project team members experienced
Impact & Recurrence: | This column indicates how critical it is to address this item and how frequently in may recur. Populate with “H”, “M”, “L”, “N” for the impact the situation has had on the project & populate with “H”, “M”, “L” for the likelihood that the situation will be experienced again based upon the definitions outlined in the legend.
IMPACT | HIGH = If Lesson not implemented, impact to customer or business will be significant.
MED = If Lesson not implemented, impact to customer or business will be noticeable and cause some hardship/work around.
LOW = If Lesson not implemented, impact to customer or business will be minimal.
NONE = If Lesson not implemented, there will be no impact to customer or business.
RECURRENCE | HIGH = This issue will definitely occur again in future projects. For positive events, we definitely want it to occur again.
MED = This issue will probably happen again in future projects.
LOW = This issue may have been a one time event.
Rank: | Based on the information discussed and captured in the table, have the team prioritize these items (using color dots, quick “show of hands” or some other pre-defined voting method). Record the relative rank for each lesson identified. Build an Action Plan to address the items that rise to highest priority.
Lessons Learned: | List in a bulleted format the lessons that the project team learned from the experience
Best Practice or Problem: | Indicate whether this lesson is a result of a positive experience that should be repeated (i.e., “best practice” or a “problem” to be fixed.
Actions Required to Implement Lessons Learned: | List is a bulleted format the specific actions that must be undertaken in order to operationalize the lesson learned
Implement: | This column identifies how soon the best practice or fix can be implemented into the project process. Populate with a “Q”, “S”, or “L” to represent if the actions required to implement the lesson learned is a “Quick Hit”, “Short-Term” or “Long-Term” goal of the project team.
QUICK HIT = Something that can be addressed quickly or used immediately without process change.
SHORT TERM = Something that may be a process change, but is small enough to be incorporated in the next 2-3 months without impact to resources.
LONG TERM = Something requiring senior management intervention and approval. Most likely impacting current process or resources.
Assigned To: | Populate with the project team member(s) that will “own” the follow-up and implementation of the lesson learned