## Workplan
Generations Working to Prevent Childhood Obesity, A Pilot Project of the Active for Life® Program
18 Month Workplan
Partnership:
Goal 1: Develop and maintain an effective partnership to promote physical activity and healthy eating for low-income children and their families.
Local Goal: To establish a strong partnership committed to a common vision in regard to XXXXXXX implementation
| Tactic 1 |  | Establish a project committee to cultivate and maintain community relationships, manage affirmation and/or modification of action plans, oversee community garden operations, assist with volunteer coordination and develop a long-term project sustainability plan, in partnership with project staff
|  | Activity 1 | Identify appropriate partners and confirm committee participation commitments
|  | Activity 2 | Hold orientation meeting and develop meeting schedule
|  | Activity 3 | Develop committee guidelines and decision-making processes to guide committee function
| Tactic 2 |  | Conduct focus groups with each stakeholder/partner group (Boys and Girls Club of the Sandhills board members, after-school program administrators and participants, parents of at-risk children, Master Gardeners and Active for Life participants) to confirm and/or modify proposed strategies and determine appealing participation incentives
|  | Activity 1 | Identifiy appropriate focus groups, participants and focus group locations
|  | Activity 2 | Develop focus group schedule and finalize focus group questions
|  | Activity 3 | Conduct focus groups and compile data to present to committee
|  | Activity 4 | Modify plans, as necessary
| Tactic 3 |  | Revise action plans and seek necessary administrative approvals for additional or modified program components, if necessary
|  | Activity 1 | Modify plan based on focus group results and committee recommendations
|  | Activity 2 | Provide modifications to each partner group for organizational review and approval
Benchmark 1 |  |  | Committee established and functioning by March 15, 2006
Benchmark 2 |  |  | XXXXXXX implementation plans finalized by April 15, 2006
Goal 2: Increase community awareness of the health and other benefits of physical activity and healthy eating for low-income children and their families.
Local Goal: Initiate efforts to increase awareness among target groups and community members at-large of active living projects specifically and the importance of healthy eating and physical activity as a whole
| Tactic 1 |  | Develop press releases and articles highlighting program initiation and progress for placement in the local newspaper, the Boys and Girls Club of the Sandhills’ quarterly “Club Reporter“ and monthly “Connections” magazine, Town of Southern Pines’ “How to Get Involved” newsletter and other similar publications
|  | Activity 1 | Develop media placement schedule
|  | Activity 2 | Identify appropriate topics of communication pieces to support/accompany achievement of activities
|  | Activity 3 | Monitor response to communications, including volunteer recruitment, community inquiries and youth participation rates
| Tactic 2 |  | Formally recruit volunteers among all past and current Active for Life participants that have an interest in gardening as physical activity through customized mailings
|  | Activity 1 | Verify mailing list
|  | Activity 2 | Develop direct mail piece
|  | Activity 3 | Track response to mailing
|  | Activity 4 | Provide volunteer follow up and orientation
| Tactic 3 |  | Create and initiate XXXXXXX youth participant recruitment campaign
|  | Activity 1 | Develop recruitment tools, including participant incentives
|  | Activity 2 | Identify AFL volunteers to assist with youth recruitment
| Tactic 4 |  | Develop and maintain signage at community garden site to promote project awareness
|  | Activity 1 | Create sign and seek necessary approvals for placement
|  | Activity 2 | Hold and facilitate press coverage for sign placement and garden dedication
Benchmark 3 |  |  | By April 1, 2006, volunteer recruitment strategies will be finalized and initiated
Benchmark 4 |  |  | By April 15, 2006, a communications plan will be in place and initiated
Goal 3: Provide phycial activity and healthy eating programs for low-income children and their families.
Local Goal: To provide the target group with healthy eating, physical activity and gardening-related education to ultimately encourage healthy lifestyles and prevent childhood obesity
| Tactic 1 |  | Provide classes to XXXXXX youth participants with education specific to gardening concepts, physical activity and healthy eating through expanded, on-site offerings of “Kids and Gardening” and “Fit Together” curricula offered by Master Gardeners, Cooperative Extension and Active for Life staff and volunteers
|  | Activity 1 | Finalize target groups and train volunteers/staff accordingly
|  | Activity 2 | Develop education calendar
|  | Activity 3 | Evaluate educational activities and youth/volunteer/staff satisfaction with educational componenets of program
Benchmark 5 |  |  | By July 15, an education calendar will be finalized and curricula offerings will be initiated
Goal 4: Enhance policy and organizational supports for physical activity and healthy eating for low-income children and their families.
Local Goal: Integrate Get Gardening! into regular operations of all partner groups through formal permanent program offerings
| Tactic 1 |  | Integrate XXXXXXX support activities into regular agency operations; for example, facilitating the adoption of “composting” as a means of food/paper waste disposal in Boys and Girls Club of the Sandhills
|  | Activity 1 | Assess opportunities for composting resources with partners
|  | Activity 2 | Assess curriculum and on-site gardening integration opportunites
| Tactic 2 |  | Monitor XXXXXXX involvement and participant satisfaction to develop a “case” for program continuation
|  | Activity 1 | Develop and disseminate quarterly updates for partner organizations
|  | Activity 2 | Develop tool for and regularly assess overall XXXXXXX participant and partner agency satisfaction
| Tactic 3 |  | Encourage of creation and adoption of a formal “sustainability” plan that includes produce sales
|  | Activity 1 | Identify elements of sustainablity plan and develop data collection calendar
|  | Activity 2 | "Test" sustainability strategies through focus groups and community events
|  | Activity 3 | Develop timeline for securing resources for ongoing operational expenses
| Tactic 4 |  | Integrate an on-site community garden tour and formal volunteer recruitment activities into Active for Life classes, specifically lesson 16, which focuses on exploring new activities
|  | Activity 1 | Provide information to facilitators on the community garden and opportunities for existing AFL participants to assist
| Tactic 5 |  | Recognize youth who regularly particpate in project and explore feasibility of forming a 4-H club and a “Junior Master Gardener” program to provide structured, long-term opportunities for project participation and youth recognition
|  | Activity 1 | Investigate requirements and feasibility of programs
|  | Activitiy 2 | Track participation in Garden and distribute rewards for high participation
|  | Activity 3 | Propose program formalization through 4-H and Junior Master Gardeners to partners and assist with implementation
Benchmark 6 |  |  | A formal sustainability plan will be submitted to the project committee for final approvals by March 1, 2007
Goal 5: Improve built environments, facilities, equipment, and other supports for physical activity and healthy eating for low-income children and their families.
Local Goal: Establish an organic community garden in Southern Pines, North Carolina
| Tactic 1 |  | Finalize agreement with Town of Southern Pines for land use, clearing and maintenance
|  | Activity 1 | Identify and establish formal agreement outlining specifics of land use, clearing and maintenance
|  | Activity 2 | Obtain final approvals, as needed
| Tactic 2 |  | Finalize garden design, including storage area for tools and compost area and purchase supplies and equipment
|  | Activity 1 | Develop final garden design, review with partners, including horticulture experts
|  | Activity 2 | Investigate storage and building options and develop appropriate plans
|  | Activity 3 | Purchase supplies and equipment
| Tactic 3 |  | Build a fence around garden, prepare land, conduct soil testing and begin planting (April 1, 2006 – April 30, 2006)
|  | Activity 1 | Purchase and install fencing equipment
|  | Activity 2 | Build raised beds and bring in soil and compost material
|  | Activity 3 | Sample and test soil; adjust soil accordingly
|  | Activity 4 | Coordinate all participant groups for planting, create schedule
| Tactic 5 |  | Conduct appropriate garden maintenance
|  | Activity 1 | Conduct weeding, watering, planting, fertilizing and clean-up on a regularly with kids and volunteers
Benchmark 7 |  |  | By May 1, 2006, XXXXXX will be established and actively worked by older adult volunteers and youth participants

## Instructions and Definitions
Generations Working to Prevent Childhood Obesity, A Pilot Project of the Active for Life® Program, Workplan Instructions
Please use the attached workplan template to list your anticipated tactics and activities for the 12 to 18 month month AFL Intergenerational project grant. Insert the text for your tactics, activities, and benchmarks in the spaces provided on the workplan template (in red). You may delete rows for tactic/activity/benchmark place-holders that are not used. Also, feel free to insert rows for additional activities or benchmarks. Please include at least one benchmark per goal.
Definitions
Goal: A general statement of a broad outcome you would like to achieve as a result of your initiative. Goal statements are generally consistent with the “5P” strategies listed below. Please do not alter the AFL Intergenerational project goals, as these will appear in the Progress Reporting System.
Tactic: A more specific statement describing the method used to help achieve a goal or goals. Tactics are specific examples of “5P” strategies.
Activity: A specific statement briefly describing an action step related to the tactic.
Benchmark: A specific, time-bound, measurable statement of a proposed concrete product or accomplishment for the upcoming project year. Example – By October 2005, submit a written report of phycial activity assessment findings to school board. Please develop at least one benchmark per goal area.
“5P” Strategies
· Preparation: Tactics that provide the groundwork and enable partnerships to work toward community change.
Examples include partnership building/maintenance, assessment, generating resources, strategic planning, community visioning.
· Promotion: Tactics intended to educate the public, media and policy-makers and increase the presence of active living messages and cues to action.
Examples include advertising, media relations, special events, internet, direct mail, branding, grassroots education, public service announcements.
· Programs: Organized efforts to encourage and provide greater opportunities for phycial activity and healthier eating.
Examples include phycial activity classes, food tastings/demonstrations, classes, incentives, gardening instruction for low income children and families.
· Policy: Tactics intended to influence changes in public policies and standards as well as organizational practices.
Examples include advocacy, relationship building with policy-makers, presentations to policy boards, influencing school policies, working with grocers to provide healthier foods.
· Physical Projects: Tactics intended to directly influence the physical environment, facilities, or provide equipment.
Examples include enhancement of existing facilities, providing playground equipment, providing equipment for preparing healthy food, community gardens.