Report

For

Class D Construction Cost

Estimate

Douglas McNeill

Director

Jon Gilford

Senior Cost Manager

Turner & Townsend

170 Laurier Avenue West

Suite 604

Ottawa

Ontario

K1P 5V5

t: +1 (613) 221 9560

- douglas.mcneill@turntown.com

- jon.gilford@turntown.com

- turnerandtownsend.com

Ottawa Public Library (OPL/LAC), Exemplar Site (Site 8) City of Ottawa

21-Nov-16

November 21, 2016

ref no. 20940

City of Ottawa

20 Metcalfe St, Ottawa,

Ontario, K1P 5M2

For the attention of Paul Hussar,

Dear Paul,

Ottawa Public Library, Exemplar Site (Site 8)

City of Ottawa

We enclose our updated Class D Construction Cost Estimate for the above‐noted based on the documentation provided to us.

Please refer to our Executive Summary, Section 1, for specific qualifications and assumptions associated with this cost report.

We trust this meets with your approval. Should you have any questions please do not hesitate to contact us.

Yours faithfully

Jon Gilford	Douglas McNeill

Senior Cost Manager	Director

Turner & Townsend	Turner & Townsend

e: jon.gilford@turntown.com	e: douglas.mcneill@turntown.com

2 of 29

Ottawa Public Library (OPL/LAC), Exemplar Site (Site 8)

City of Ottawa

Contents

- EXECUTIVE SUMMARY

- ELEMENTAL ESTIMATE

- AREA SUMMARY

- DOCUMENT LIST

|  | Rev | Originator | Approved | Date |
| --- | --- | --- | --- | --- |
|  | 2 | Jon Gilford | Marcos Sibal | Sep. 23rd, 2016 |
|  | 3 | Sopanna Surendran | Haneef Ahmed | October 6th, 2016 |
|  | 4 | Sopanna Surendran | Haneef Ahmed | October 21st, 2016 |
|  | 5 | Sopanna Surendran | Haneef Ahmed | October 24th, 2016 |
|  | 6 | Sopanna Surendran | Haneef Ahmed | October 25th, 2016 |
|  | 7 | Sopanna Surendran | Haneef Ahmed | October 27th, 2016 |
|  | 8 |  | Haneef Ahmed | November 2, 2016 |
|  | 9 |  | Haneef Ahmed | November 17, 2016 |
|  | 9 |  | Haneef Ahmed | November 21, 2016 |

© Turner & Townsend. All rights reserved Nov 16. This document is expressly provided to and solely for the use of the City of Ottawa. and must not be quoted from, referred to, used by or distributed to any other party without the prior consent of Turner & Townsend who accept no liability of whatsoever nature for any use by any other party.

F:\Tor\Jobs\2014 Jobs - 20860 -\20940 CM - Ottawa Public Library - NK\2016 Estimate\200 Class D Exemplar Site - July 2016\Estimate\Revised Sep + Oct, 2016\Updated , 2016\Nov 16 2016\[OPL LAC r9 Nov 16.xlsx]Sum (2)

3 of 29

Ottawa Public Library (OPL/LAC), Exemplar Site (Site 8)

The purpose of this Cost Plan is to provide the City of Ottawa

City of Ottawa

- EXECUTIVE SUMMARY

1.1	Introduction

Turner and Townsend is retained to provide Cost Planning & Design Cost Control services, including preparation of this Class D Construction Cost Analysis, based on the information listed in Section 5. Our estimate is an Opinion of Probable Cost only and reflects current local market rates based on normal competitive conditions. Our estimate is intended to be comparable to a range of bids received from a number of competitive general contractors and sub‐trades.

Turner and Townsend does not guarantee that tenders or actual construction costs will not vary from this estimate. Adverse market conditions, proprietary and/or sole source specifications, single sourcing of materials and equipment or reduced competition among contractors may cause bids to vary from reasonable estimates based on normal competitive conditions.

with a budget framework within

which the project can be developed and cost managed, from Feasibility to Tender award stage.

The Cost Plan has been prepared solely in accordance with the documentation outlined within this document.

This Cost Plan is subject to review, confirmation and/or amendments following revisions to the information stated and discussion(s) with the Client and Design Consultants at which time this report will be reviewed and may be re-issued if required.

1.2	Procurement and Schedule

The Construction Cost Estimate includes all direct construction costs and contractor’s overhead and profit. It assumes that the project will be procured on a Stipulated Lump sum

basis, and that bids will be received from a minimum of five pre‐qualified general contractors. We also assume that the project will be completed in a reasonable time frame and have not included any premiums related to “fast‐tracking” the project, if required. The unit rates in our estimate are based on construction activities occurring during normal working hours and proceeding within a non‐accelerated schedule.

4 of 29

Ottawa Public Library (OPL/LAC), Exemplar Site (Site 8)

City of Ottawa

1.3	Risk Assessment

Pricing reflects 4Q 2016 rates and present market/local conditions. Escalation allowance to the anticipated construction start date of 3Q 2019 has been included within our cost analysis at 10%.

The estimate includes an Estimating/Design Contingency Allowance to account for increases in cost as a result of design development through to 100% complete tender documentation.

Post-Contract Contingency (i.e. for Change Directives/Change Orders that may arise during construction) has been included in our cost report at 10%.

We have not accounted for a construction market allowance within the report, however based upon our past and ongoing construction cost project experience in Ottawa, Ontario, we do not

foresee any risk of receiving non‐competitive bids from major sub – trades.

1.4	Level of Documentation and Assumptions

The estimate is based on the conceptual / preliminary drawings as well as functional program provided. It is supplemented by correspondence and discussions with the Owner and Design Consultants.

We outline some of the major assumptions we have made with respect to this cost analysis:-

- Project to be procured via Stipulated Lump Sum contract

- No major phasing requirements

- No ‘Accelerated’ schedule premiums allowed

5 of 29

Ottawa Public Library (OPL/LAC), Exemplar Site (Site 8)

City of Ottawa

1.5	Measurement and Pricing

The estimate has been developed using generally accepted principles on method of measurement as per the Canadian Institute of Quantity Surveyors Elemental Cost Analysis (CIQS).

The rates used for this estimate include labour and material, equipment, and subcontractor’s overheads and profit. Pricing developed for this project is based upon our company’s experience with similar projects, and/or quotes provided by subcontractors and suppliers as noted within the estimate. It does not take into account extraordinary market conditions, where bidders may be limited and may include in their tenders disproportionate contingencies and profit margins.

1.6	General Conditions and Fee

The fee included within the estimate for the General Contractor is included as a percentage of the hard construction cost. The general requirements are based on our assumptions of the anticipated construction approach and construction schedule for the project (see section 1.2). The general requirements percentage includes the cost associated with bonding and insurance, however excludes development and/or building permit costs.

6 of 29

Ottawa Public Library (OPL/LAC), Exemplar Site (Site 8)

City of Ottawa

1.7	Taxes

Our cost estimate includes HST (1.76%).

1.8	General Statement of Liability

This report is not intended for general circulation, publication or reproduction for any other person or purpose without prior express written permission to each specific instance.

Furthermore, this report was written for the exclusive use of City of Ottawa and is not to be relied upon by any other party. Turner and Townsend does not hold any reporting responsibility to any other party.

Turner and Townsend strongly recommends the owner and/or design team review the cost estimate report including line item descriptions, unit prices, allowances, assumptions, exclusions, and contingencies to ensure the appropriate design intent has been accurately captured within the report.

7 of 29

Project No. 20940

Rev. R9

Nov 21, 2016

OTTAWA PUBLIC LIBRARY (OPL/LAC) - Exemplar Site (Site 8)

CLASS D COST ANALYSIS

EXECUTIVE SUMMARY COST BREAKDOWN

| Construction Cost Breakdown: | GFA (sf) | $/sf | Amount |
| --- | --- | --- | --- |

- BELOW GRADE PARKING:

| A.1 | Below Grade Parking Cost | 71,532 | $184 | $13,151,000 |
| --- | --- | --- | --- | --- |
| A.2 | Escalation Allowance (10%) - 3Q 2019 |  |  | Included |
| A.3 | Construction Contingency Allowance - Post Contract (10%) |  |  | Included |
| A.4 | Furniture, Furnishings and Equipment - NIC |  |  | Excluded |
| A.5 | LEED Gold Allowance (5%) |  |  | $658,000 |
| A.6 | HST | 1.76% |  | $243,000 |
|  | A. Sub-total Below Grade Parking | 71,532 | $196 | $14,052,000 |

- BUILDING:

| B.1 | OPL Costs | 99,211 | $545 | $54,051,000 |
| --- | --- | --- | --- | --- |
| B.2 | LAC Costs | 54,774 | $559 | $30,624,000 |
| B.3 | Shared Space Costs - OPL | 33,571 | $556 | $18,667,000 |
| B.4 | Shared Space Costs - LAC | 27,902 | $554 | $15,466,000 |
|  | Sub-Total | 215,458 | $551 | $118,808,000 |
| B.5 | Escalation Allowance (10%) - 3Q 2019 |  |  | Included |
| B.6 | Construction Contingency Allowance - Post Contract (10%) |  |  | Included |
|  | Total Construction Cost | 215,458 | $551 | $118,808,000 |
| B.7 | Furniture, Furnishings and Equipment - NIC |  |  | Excluded |
| B.8 | LEED Gold Allowance (5%) |  |  | $5,940,000 |
|  | Total Construction Cost - Including LEED premiums | 215,458 | $579 | $124,748,000 |
| B.9 | HST | 1.76% |  | $2,196,000 |
|  | B. Sub-total Building | 215,458 | $589 | $126,944,000 |
|  | Total Estimated Construction Cost (A+B), incl HST | 286,990 | $491 | $140,996,000 |

Notes/Assumptions:

1 The above is an opinion of Probable Cost Only

2 Construction contingency included at 10%

3 Escalation allowance of 10% included to 3Q 2019

4 Understanding that the ground is contaminated and may contain rock. An allowance has been made but this should be re-evaluated on receipt of a geotechnical report

5 Allowance for LEED Gold

6 Sloping site and cost allowed to reflect cut and fill

7 1 levels of parking (level 0 included)

8 2 oversized freight elevators and 9 standard elevators allowed for

9 UV Films to windows - LAC - allowed for 40% of curtain wall

10 Acoustic treatment to ceiling / wall

11 We allow for Management of Ground Water and Pumping only for Construction

12 Storm Water Cistern assume 50m3 (Water Retention)

13 We have carried some allowances for utility relocation (scope unknown)

14 Layby Cost covered within the Site Development Cost

15 Allowance for Smoke vac to Atrium

8 of 29

The following have been specifically excluded:

1 Professional Consultant Design Fees

2 Specialist Consultant Design Fees

3 Legal Fees and Expenses

4 Project Management Fees

5 Furniture, Furnishings and Equipment (other than detailed in the estimate)

6 Owner's Administration Expenses

7 Library equipment - book shelves / sorter / mobile shelving etc

8 Permits and Development Charges

9 Garbage Equipment/Bins

10 Food Equipment/Kitchen Equipment

11 Construction Price Escalation Beyond - 3Q 2019

12 A/V/head end Equipment

13 IT & Communication Equipment

14 Premiums for Single Sourced Materials

15 Schedule Acceleration Premium

16 Emergency Generator

17 Land Acquisition Cost

18 Major Sitework Other Than Allowance Noted In The Estimate

19 Moving Cost

- Artwork

- Automated Blinds

- No allowance for demolition or alterations

- Raised Floor, Stage

- Removal of Contaminated Soils - Budget Provided by Golder

- High Density Shelving

- Allowance for work to CSST

9 of 29

Ottawa Public Library (OPL/LAC), Exemplar Site (Site 8)

City of Ottawa

- ELEMENTAL ESTIMATE

10 of 29

ELEMENTAL COST SUMMARY

CLASS D COST ANALYSIS

|  |  |  |  |  |  |  |  |  | Cat: |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project: |  | OTTAWA PUBLIC LIBRARY (OPL/LAC) - Exemplar Site (Site 8) - Parking |  |  |  |  |  |  | File: | SS-DD-R9 |  |
| Location: |  | Ottawa, Ontario |  |  |  |  |  |  | Date: | Nov 21, 2016 |  |
| Owner/Client: |  | City of Ottawa |  |  |  |  |  |  | Project Number: | 20940 |  |
| Architect: |  | Ajon Moryiama |  |  |  |  |  |  | Gross Floor Area: | 71,532 sf |  |
|  |  |  |  | Ratio | Elemental | Elemental |  | Elemental |  |  |  |
| Element |  |  |  | to GFA | Quantity | Unit Rate |  | Amount | Cost/sf | Amount |  |
| A SHELL |  |  |  |  |  |  |  |  |  |  |  |
| A1 SUBSTRUCTURE |  |  |  |  |  |  |  |  | $22.75 |  |  |
| A11 | Foundation |  |  | 1.00 | 71,532 sf | $0.00 |  | $0 | $0.00 | $1,627,000 | 12% |
| A12 | Basement Excavation |  |  | 0.65 | 46,498 cy | $34.99 |  | $1,627,000 | $22.75 |  |  |
| A2 STRUCTURE |  |  |  |  |  |  |  |  | $35.17 |  |  |
| A21 | Lowest Floor Construction |  |  | 1.00 | 71,532 sf | $11.51 |  | $823,000 | $11.51 |  |  |
| A22 | Upper Floor Construction |  |  | 0.00 | 0 sf | $0.00 |  | $0 | $0.00 | $2,516,000 | 19% |
| A23 | Roof Construction |  |  | 0.14 | 9,705 sf | $174.45 |  | $1,693,000 | $23.67 |  |  |
| A3 EXTERIOR ENCLOSURE |  |  |  |  |  |  |  |  | $22.86 |  |  |
| A31 | Walls Below Grade |  |  | 0.26 | 18,292 sf | $37.39 |  | $684,000 | $9.56 |  |  |
| A32 | Walls Above Grade |  |  | 0.00 | 0 sf | $0.00 |  | $0 | $0.00 |  |  |
| A33 | Windows & Entrances |  |  | 0.00 | 2 sf | $25,000.00 |  | $50,000 | $0.70 |  |  |
| A34 | Roof Covering |  |  | 0.14 | 9,705 sf | $67.08 |  | $651,000 | $9.10 | $1,635,000 | 12% |
| A35 | Projections |  |  | 1.00 | 71,532 sf | $3.49 |  | $250,000 | $3.49 |  |  |
| B INTERIORS |  |  |  |  |  |  |  |  |  |  |  |
| B1 PARTITIONS & DOORS |  |  |  |  |  |  |  |  | $3.47 |  |  |
| B11 | Partitions |  |  | 0.07 | 5,007 sf | $39.94 |  | $200,000 | $2.80 | $248,000 | 2% |
| B12 | Doors |  |  | 0.00 | 24 No | $2,004.69 |  | $48,000 | $0.67 |  |  |
| B2 FINISHES |  |  |  |  |  |  |  |  | $8.01 |  |  |
| B21 | Floor Finishes |  |  | 1.00 | 71,532 sf | $4.50 |  | $322,000 | $4.50 |  |  |
| B22 | Ceiling Finishes |  |  | 1.00 | 71,532 sf | $2.50 |  | $179,000 | $2.50 | $573,000 | 4% |
| B23 | Wall Finishes |  |  | 1.00 | 71,532 sf | $1.01 |  | $72,000 | $1.01 |  |  |
| B3 FITTINGS & EQUIPMENT |  |  |  |  |  |  |  |  | $2.50 |  |  |
| B31 | Fittings & Fixtures |  |  | 1.00 | 71,532 sf | $2.50 |  | $179,000 | $2.50 |  |  |
| B32 | Equipment |  |  | 1.00 | 71,532 sf | $0.00 |  | $0 | $0.00 | $179,000 | 1% |
| B33 | Conveying Systems |  |  | 0.00 | 0 Stp | $0.00 |  | $0 | $0.00 |  |  |
| C SERVICES |  |  |  |  |  |  |  |  |  |  |  |
| C1 MECHANICAL |  |  |  |  |  |  |  |  | $11.00 |  |  |
| C11 | Plumbing & Drainage |  |  | 1.00 | 71,532 sf | $3.49 |  | $250,000 | $3.49 |  |  |
| C12 | Fire Protection |  |  | 1.00 | 71,532 sf | $3.01 |  | $215,000 | $3.01 |  |  |
| C13 | H.V.A.C. |  |  | 1.00 | 71,532 sf | $3.49 |  | $250,000 | $3.49 | $787,000 | 6% |
| C14 | Controls |  |  | 1.00 | 71,532 sf | $1.01 |  | $72,000 | $1.01 |  |  |
| C2 ELECTRICAL |  |  |  |  |  |  |  |  | $11.51 |  |  |
| C21 | Service & Distribution |  |  | 1.00 | 71,532 sf | $4.50 |  | $322,000 | $4.50 |  |  |
| C22 | Lighting, Devices & Heating |  |  | 1.00 | 71,532 sf | $5.00 |  | $358,000 | $5.00 | $823,000 | 6% |
| C23 | Systems & Ancillaries |  |  | 1.00 | 71,532 sf | $2.00 |  | $143,000 | $2.00 |  |  |
| NET BUILDING COST (Excluding Site) |  |  |  |  |  |  |  |  | $117.26 | $8,388,000 | 64% |
| D SITE & ANCILLARY WORK |  |  |  |  |  |  |  |  |  |  |  |
| D1 SITE WORK |  |  |  |  |  |  |  |  | $0.00 |  |  |
| D11 Site Development |  |  |  | 0.00 | 0 sf | $0.00 |  | $0 | $0.00 |  |  |
| D12 Mechanical Site Services |  |  |  | 0.00 | 0 sf | $0.00 |  | $0 | $0.00 | $0 | 0% |
| D13 Electrical Site Services |  |  |  | 0.00 | 0 sf | $0.00 |  | $0 | $0.00 |  |  |
| D2 ANCILLARY WORK |  |  |  |  |  |  |  |  | $0.00 |  |  |
| D21 Demolition |  |  |  | 0.00 | 0 sf | $0.00 |  | $0 | $0.00 | $0 | 0% |
| D22 Alterations |  |  |  | 0.00 | 0 sf | $0.00 |  | $0 | $0.00 |  |  |
| NET BUILDING COST (Including Site) |  |  |  |  |  |  |  |  | $117.26 | $8,388,000 |  |
| Z GENERAL REQUIREMENTS & ALLOWANCES |  |  |  |  |  |  |  |  |  |  |  |
| Z1 GEN. REQ. & FEE |  |  | 12.0% |  |  |  |  |  | $14.08 |  |  |
| Z11 | General Requirements |  | 9.0% |  |  |  |  | $755,000 | $10.55 | $1,007,000 | 8% |
| Z12 | Fee |  | 3.0% |  |  |  |  | $252,000 | $3.52 |  |  |
| TOTAL CONSTRUCTION ESTIMATE (Excluding Allowances) |  |  |  |  |  |  |  |  |  | $9,395,000 | 71% |
| Z2 ALLOWANCES |  |  | 40.0% |  |  |  |  |  | $52.51 |  |  |
| Z21 | Estimating Allowance |  | 20.0% |  |  |  |  | $1,878,000 | $26.25 |  |  |
| Z22 | Escalation Allowance |  | 10.0% 3Q 2019 |  |  |  |  | $939,000 | $13.13 | $3,756,000 | 29% |
| Z23 | Construction Allowance |  | 10.0% |  |  |  |  | $939,000 | $13.13 |  |  |
| TOTAL CONSTRUCTION ESTIMATE (Including Allowances) |  |  |  |  |  |  |  |  |  | $13,151,000 | 100% |
|  |  |  |  |  |  |  |  |  |  | Cost/unit |  |
| GFA |  | 71,532 sf |  |  |  |  |  |  |  | $184 | sf |
| GFA |  | 6,645 m2 |  |  |  |  |  |  |  | $1,979 | m2 |

11 of 29

|  | Project: OTTAWA PUBLIC LIBRARY (OPL/LAC) - Exemplar Site (Site 8) - Parking |  |  |  | File: SS-DD-R9 |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Location: Ottawa, Ontario |  |  |  | Date: Nov 21, 2016 |  |
|  | Owner/Client: City of Ottawa |  |  | Project Number: 20940 |  |  |
|  | Architect: Ajon Moryiama |  |  | Gross Floor Area: 71532 sf |  |  |
|  | Description |  | Quantity |  | Rate | Amount |
|  | GROSS FLOOR AREA |  |  |  |  |  |
|  | TOTAL GROSS FLOOR AREA |  | 71,532 sf |  |  |  |
|  |  |  | 71,532 sf |  |  |  |
|  | A1 SUBSTRUCTURE |  |  |  |  |  |
|  | A11 Foundations |  |  |  |  |  |
|  | TOTAL A11 Foundations |  | 71,532 sf |  | 0.00 | 0 |
|  | A12 Basement Excavation |  |  |  |  |  |
|  | Below grade parking |  | 71,532 sf |  | 22.75 | 1,627,460 |
|  | TOTAL A12 Basement Excavation |  | 46,498 cy |  | 34.99 | 1,627,000 |
|  | TOTAL A1 SUBSTRUCTURE |  |  |  |  |  |
|  |  |  |  |  |  | 1,627,000 |
|  | A2 STRUCTURE |  |  |  |  |  |
|  | A21 Lowest Floor Construction |  |  |  |  |  |
|  | Below grade parking | + | 71,532 sf |  | 11.50 | 822,610 |
|  | TOTAL A21 Lowest Floor Construction |  | 71,532 sf |  | 11.51 | 823,000 |
|  | A22 Upper Floor Construction |  |  |  |  |  |
|  | Below grade parking - not required |  | 71,532 sf |  |  |  |
|  | TOTAL A22 Upper Floor Construction |  | 0 sf |  | 0.00 | 0 |
|  | A23 Roof Construction |  |  |  |  |  |
|  | Below grade parking |  | 71,532 sf |  | 23.67 | 1,693,090 |
|  | Suspended slab | + | 9,705 sf |  | 50.00 |  |
|  | TOTAL A23 Roof Construction |  | 9,705 sf |  | 174.45 | 1,693,000 |
|  | TOTAL A2 STRUCTURE |  |  |  |  |  |
|  |  |  |  |  |  | 2,516,000 |
|  | A3 EXTERIOR ENCLOSURE |  |  |  |  |  |
|  | A31 Walls Below Grade |  |  |  |  |  |
|  | Below grade parking |  | 71,532 sf |  | 9.56 | 683,710 |

12 of 29

|  | Project: OTTAWA PUBLIC LIBRARY (OPL/LAC) - Exemplar Site (Site 8) - Parking |  |  |  | File: SS-DD-R9 |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Location: Ottawa, Ontario |  |  |  | Date: Nov 21, 2016 |  |
|  | Owner/Client: City of Ottawa |  |  | Project Number: 20940 |  |  |
|  | Architect: Ajon Moryiama |  |  | Gross Floor Area: 71532 sf |  |  |
|  | Description |  | Quantity |  | Rate | Amount |
|  | TOTAL A31 Walls Below Grade |  | 18,292 sf |  | 37.39 | 684,000 |
|  | A32 Walls Above Grade |  |  |  |  |  |
|  | Below grade parking - not required |  | 71,532 sf |  |  |  |
|  | TOTAL A32 Walls Above Grade |  | 0 sf |  | 0.00 | 0 |
|  | A33 Windows & Entrances |  |  |  |  |  |
|  | Below grade parking |  | 71,532 sf |  | 0.70 | 50,000 |
|  | Overhead doors - 2 no - Parking | + | 2 no | 25000.00 |  |  |
|  | TOTAL A33 Windows & Entrances |  | 2 no | 25000.00 |  | 50,000 |
|  | A34 Roof Covering |  |  |  |  |  |
|  | Below grade parking |  | 71,532 |  | 7.10 | 651,090 |
|  | Roof covering | + | 9,705 sf |  | 15.00 |  |
|  | TOTAL A34 Roof Covering |  | 9,705 sf |  | 67.08 | 651,000 |
|  | A35 Projections |  |  |  |  |  |
|  | Below grade parking |  | 71,532 sf |  | 3.49 | 250,000 |
|  | Ramp formation |  | 1 sum | 150000.00 |  |  |
|  | Loading dock |  | 1 sum | 100000.00 |  |  |
|  | TOTAL A35 Projections |  | 71,532 sf |  | 3.49 | 250,000 |
|  | TOTAL A3 EXTERIOR ENCLOSURE |  |  |  |  |  |
|  |  |  |  |  |  | 1,635,000 |
|  | TOTAL A SHELL |  |  |  |  |  |
|  |  |  |  |  |  | 5,778,000 |
|  | B1 PARTITIONS & DOORS |  |  |  |  |  |
|  | B11 Partitions |  |  |  |  |  |
|  | Below grade parking |  | 71,532 sf |  | 2.80 | 200,290 |
|  | Allowance for partition | + | 5,007 sf |  | 40.00 |  |
|  | TOTAL B11 Partitions |  | 5,007 sf |  | 39.94 | 200,000 |
|  | B12 Doors |  |  |  |  |  |
|  | Below grade parking |  | 71,532 sf |  | 0.67 | 48,000 |
|  | Allowance for hollow metal doors | + | 24 no |  | 2000.00 |  |
|  | TOTAL B12 Doors |  | 24 no | 2004.69 |  | 48,000 |

13 of 29

|  | Project: OTTAWA PUBLIC LIBRARY (OPL/LAC) - Exemplar Site (Site 8) - Parking |  |  |  | File: SS-DD-R9 |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Location: Ottawa, Ontario |  |  |  | Date: Nov 21, 2016 |  |
|  | Owner/Client: City of Ottawa |  |  | Project Number: 20940 |  |  |
|  | Architect: Ajon Moryiama |  |  | Gross Floor Area: 71532 sf |  |  |
|  | Description |  |  | Quantity | Rate | Amount |
|  | TOTAL B1 PARTITIONS & DOORS |  |  |  |  |  |
|  |  |  |  |  |  | 248,000 |
|  | B2 FINISHES |  |  |  |  |  |
|  | B21 Floor Finishes |  |  |  |  |  |
|  | Below grade parking |  |  | 71,532 sf | 4.50 | 321,890 |
|  | Allowance for traffic topping - Below Grade Parking |  | + | 71,532 sf | 4.50 |  |
|  | TOTAL | B21 Floor Finishes |  | 71,532 sf | 4.50 | 322,000 |
|  | B22 Ceiling Finishes |  |  |  |  |  |
|  | Below grade parking |  | + | 71,532 sf | 2.50 | 178,830 |
|  | Paint to exposed structure |  |  | 71,532 sf | 2.50 |  |
|  | TOTAL | B22 Ceiling Finishes |  | 71,532 sf | 2.50 | 179,000 |
|  | B23 Wall Finishes |  |  |  |  |  |
|  | Below grade parking |  | + | 71,532 sf | 1.00 | 71,530 |
|  | Paint to wall |  |  | 71,532 sf | 1.00 |  |
|  | TOTAL | B23 Wall Finishes |  | 71,532 sf | 1.01 | 72,000 |
|  | TOTAL | B2 FINISHES |  |  |  |  |
|  |  |  |  |  |  | 573,000 |
|  | B3 FITTINGS & EQUIPMENT |  |  |  |  |  |
|  | B31 Fittings & Fixtures |  |  |  |  |  |
|  | Below grade parking |  |  | 71,532 sf | 2.50 | 178,830 |
|  | Allowance |  | + | 71,532 sf | 2.50 |  |
|  | TOTAL | B31 Fittings & Fixtures |  | 71,532 sf | 2.50 | 179,000 |
|  | B32 Equipment |  |  |  |  |  |
|  | TOTAL | B32 Equipment |  | 71,532 sf | 0.00 | 0 |
|  | B33 Conveying Systems |  |  |  |  |  |
|  | Below grade parking |  |  | 71,532 sf |  |  |
|  | TOTAL | B33 Conveying Systems |  | 0 Stp | 0.00 | 0 |
|  | TOTAL B3 FITTINGS & EQUIPMENT |  |  |  |  |  |
|  |  |  |  |  |  | 179,000 |
|  | TOTAL B INTERIORS |  |  |  |  |  |
|  |  |  |  |  |  | 1,000,000 |

14 of 29

|  | Project: OTTAWA PUBLIC LIBRARY (OPL/LAC) - Exemplar Site (Site 8) - Parking |  | File: SS-DD-R9 |  |
| --- | --- | --- | --- | --- |
|  | Location: Ottawa, Ontario |  | Date: Nov 21, 2016 |  |
|  | Owner/Client: City of Ottawa | Project Number: 20940 |  |  |
|  | Architect: Ajon Moryiama | Gross Floor Area: 71532 sf |  |  |
|  | Description | Quantity | Rate | Amount |
|  | C1 MECHANICAL |  |  |  |
|  | C11 Plumbing & Drainage |  |  |  |
|  | Allowance |  |  |  |
|  | Below grade parking | 71,532 sf | 3.50 | 250,360 |
|  | TOTAL C11 Plumbing & Drainage | 71,532 sf | 3.49 | 250,000 |
|  | C12 Fire Protection |  |  |  |
|  | Allowance |  |  |  |
|  | Below grade parking | 71,532 sf | 3.00 | 214,600 |
|  | TOTAL C12 Fire Protection | 71,532 sf | 3.01 | 215,000 |
|  | C13 HVAC |  |  |  |
|  | Allowance |  |  |  |
|  | Below grade parking | 71,532 sf | 3.50 | 250,360 |
|  | TOTAL C13 HVAC | 71,532 sf | 3.49 | 250,000 |
|  | C14 Controls |  |  |  |
|  | Allowance |  |  |  |
|  | Below grade parking | 71,532 sf | 1.00 | 71,530 |
|  | TOTAL C14 Controls | 71,532 sf | 1.01 | 72,000 |
|  | TOTAL C1 MECHANICAL |  |  |  |
|  |  |  |  | 787,000 |
|  | C2 ELECTRICAL |  |  |  |
|  | C21 Service & Distribution |  |  |  |
|  | Allowance |  |  |  |
|  | Below grade parking | 71,532 sf | 4.50 | 321,890 |
|  | TOTAL C21 Service & Distribution | 71,532 sf | 4.50 | 322,000 |
|  | C22 Lighting, Devices & Heating |  |  |  |
|  | Allowance |  |  |  |
|  | Below grade parking | 71,532 sf | 5.00 | 357,660 |
|  | TOTAL C22 Lighting, Devices & Heating | 71,532 sf | 5.00 | 358,000 |
|  | C23 Systems & Ancillaries |  |  |  |
|  | Allowance |  |  |  |
|  | Below grade parking | 71,532 sf | 2.00 | 143,060 |

15 of 29

|  | Project: OTTAWA PUBLIC LIBRARY (OPL/LAC) - Exemplar Site (Site 8) - Parking |  | File: SS-DD-R9 |  |
| --- | --- | --- | --- | --- |
|  | Location: Ottawa, Ontario |  | Date: Nov 21, 2016 |  |
|  | Owner/Client: City of Ottawa | Project Number: 20940 |  |  |
|  | Architect: Ajon Moryiama | Gross Floor Area: 71532 sf |  |  |
|  | Description | Quantity | Rate | Amount |
|  | TOTAL C23 Systems & Ancillaries | 71,532 sf | 2.00 | 143,000 |
|  | TOTAL C2 ELECTRICAL |  |  |  |
|  |  |  |  | 823,000 |
|  | TOTAL C SERVICES |  |  |  |
|  |  |  |  | 1,610,000 |
|  | NET BUILDING COST (EXCLUDING SITE) |  |  |  |
|  |  |  |  | 8,388,000 |
|  | D1 SITE WORK |  |  |  |
|  | D11 Site Development |  |  |  |
|  | Below grade parking | 71,532 sf |  |  |
|  | TOTAL D11 Site Development | 0 sf | 0.00 | 0 |
|  | D12 Mechanical Site Services |  |  |  |
|  | Below grade parking | 71,532 sf |  |  |
|  | TOTAL D12 Mechanical Site Services | 0 sf | 0.00 | 0 |
|  | D13 Electrical Site Services |  |  |  |
|  | Below grade parking | 71,532 sf |  |  |
|  | TOTAL D13 Electrical Site Services | 0 sf | 0.00 | 0 |
|  | TOTAL D1 SITE WORK |  |  |  |
|  |  |  |  | 0 |
|  | D2 ANCILLARY WORK |  |  |  |
|  | D21 Demolition |  |  |  |
|  | TOTAL D21 Demolition | sf | 0.00 | 0 |
|  | D22 Alterations |  |  |  |
|  | N/A |  |  |  |
|  | TOTAL D22 Alterations | 0 sf | 0.00 | 0 |
|  | TOTAL D2 ANCILLARY WORK |  |  |  |
|  |  |  |  | 0 |
|  | TOTAL D SITE & ANCILLARY WORK |  |  |  |
|  |  |  |  | 0 |
|  | NET BUILDING COST (INCLUDING SITE) |  |  |  |
|  |  |  |  | 8,388,000 |
|  | Z1 GENERAL REQUIREMENTS & FEE |  |  |  |
|  | Z11 General Requirements |  |  |  |

16 of 29

| Project: OTTAWA PUBLIC LIBRARY (OPL/LAC) - Exemplar Site (Site 8) - Parking |  |  | File: SS-DD-R9 |  |
| --- | --- | --- | --- | --- |
| Location: Ottawa, Ontario |  |  | Date: Nov 21, 2016 |  |
| Owner/Client: City of Ottawa |  | Project Number: 20940 |  |  |
| Architect: Ajon Moryiama |  | Gross Floor Area: 71532 sf |  |  |
| Description |  | Quantity | Rate | Amount |
| General Requirements |  | ls |  | 755,000 |
| TOTAL Z11 General Requirements |  |  |  | 755,000 |
| Z12 Fee |  |  |  |  |
| Fee |  | ls |  | 252,000 |
| TOTAL Z12 Fee |  |  |  | 252,000 |
| TOTAL Z1 GENERAL REQUIREMENTS & FEE |  |  |  |  |
|  |  |  |  | 1,007,000 |
| TOTAL CONSTRUCTION ESTIMATE EXCLUDING ALLOWANCES |  |  |  |  |
|  |  |  |  | 9,395,000 |
| Z2 CONTINGENCIES |  |  |  |  |
| Z21 Estimating Contingency |  |  |  |  |
| Estimating Contingency |  | ls |  | 1,878,000 |
| TOTAL Z21 Estimating Contingency |  |  |  | 1,878,000 |
| Z22 Escalation Contingency |  |  |  |  |
| Escalation Contingency |  | ls |  | 939,000 |
| TOTAL Z22 Escalation Contingency |  |  |  | 939,000 |
| Z23 Construction Contingency |  |  |  |  |
| Construction Contingency |  | ls |  | 939,000 |
| Total Z23 Construction Contingency |  |  |  | 939,000 |
| TOTAL Z2 CONTINGENCIES |  |  |  |  |
|  |  |  |  | 3,756,000 |
| TOTAL Z GENERAL REQUIREMENTS & CONTINGENCIES |  |  |  |  |
|  |  |  |  | 4,763,000 |
| TOTAL BUILDING COST INCLUDING ALLOWANCES |  |  |  |  |
|  |  |  |  | 13,151,000 |

17 of 29

ELEMENTAL COST SUMMARY

CLASS D COST ANALYSIS

| Project: |  | OTTAWA PUBLIC LIBRARY (OPL/LAC) - Exemplar Site (Site 8) - Above Grade |  |  |  |  |  | Cat: |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | File: | SS-DD-R9 |  |
| Location: |  | Ottawa, Ontario |  |  |  |  |  | Date: | Nov 21, 2016 |  |
| Owner/Client: |  | City of Ottawa |  |  |  |  |  | Project Number: | 20940 |  |
| Architect: |  | Ajon Moryiama |  |  |  |  |  | Gross Floor Area: | 215,458 sf |  |
|  |  |  |  | Ratio | Elemental | Elemental | Elemental |  |  |  |
| Element |  |  |  | to GFA | Quantity | Unit Rate | Amount | Cost/sf | Amount |  |
| A SHELL |  |  |  |  |  |  |  |  |  |  |
| A1 SUBSTRUCTURE |  |  |  |  |  |  |  | $8.02 |  |  |
| A11 | Foundation |  |  | 0.11 | 24,156 sf | $48.81 | $1,179,000 | $5.47 | $1,729,000 | 1% |
| A12 | Basement Excavation |  |  | 0.22 | 46,498 cy | $11.83 | $550,000 | $2.55 |  |  |
| A2 STRUCTURE |  |  |  |  |  |  |  | $62.82 |  |  |
| A21 | Lowest Floor Construction |  |  | 0.11 | 24,156 sf | $11.51 | $278,000 | $1.29 |  |  |
| A22 | Upper Floor Construction |  |  | 0.89 | 191,302 sf | $53.14 | $10,165,000 | $47.18 | $13,534,000 | 11% |
| A23 | Roof Construction |  |  | 0.29 | 61,827 sf | $49.99 | $3,091,000 | $14.35 |  |  |
| A3 EXTERIOR ENCLOSURE |  |  |  |  |  |  |  | $53.26 |  |  |
| A31 | Walls Below Grade |  |  | 0.08 | 18,292 sf | $12.63 | $231,000 | $1.07 |  |  |
| A32 | Walls Above Grade |  |  | 0.20 | 42,300 sf | $60.00 | $2,538,000 | $11.78 |  |  |
| A33 | Windows & Entrances |  |  | 0.12 | 26,392 sf | $156.30 | $4,125,000 | $19.15 |  |  |
| A34 | Roof Covering |  |  | 0.29 | 61,827 sf | $62.03 | $3,835,000 | $17.80 | $11,476,000 | 10% |
| A35 | Projections |  |  | 1.00 | 215,458 sf | $3.47 | $747,000 | $3.47 |  |  |
| B INTERIORS |  |  |  |  |  |  |  |  |  |  |
| B1 PARTITIONS & DOORS |  |  |  |  |  |  |  | $27.86 |  |  |
| B11 | Partitions |  |  | 0.81 | 174,521 sf | $29.80 | $5,201,000 | $24.14 | $6,002,000 | 5% |
| B12 | Doors |  |  | 0.00 | 400 No | $2,000.10 | $801,000 | $3.72 |  |  |
| B2 FINISHES |  |  |  |  |  |  |  | $45.57 |  |  |
| B21 | Floor Finishes |  |  | 1.00 | 215,458 sf | $18.86 | $4,064,000 | $18.86 |  |  |
| B22 | Ceiling Finishes |  |  | 1.00 | 215,458 sf | $14.99 | $3,230,000 | $14.99 | $9,818,000 | 8% |
| B23 | Wall Finishes |  |  | 2.62 | 563,455 sf | $4.48 | $2,524,000 | $11.71 |  |  |
| B3 FITTINGS & EQUIPMENT |  |  |  |  |  |  |  | $38.30 |  |  |
| B31 | Fittings & Fixtures |  |  | 1.00 | 215,458 sf | $26.60 | $5,732,000 | $26.60 |  |  |
| B32 | Equipment |  |  | 1.00 | 215,458 sf | $1.16 | $250,000 | $1.16 | $8,252,000 | 7% |
| B33 | Conveying Systems |  |  | 0.00 | 48 Stp | $47,291.67 | $2,270,000 | $10.54 |  |  |
| C SERVICES |  |  |  |  |  |  |  |  |  |  |
| C1 MECHANICAL |  |  |  |  |  |  |  | $59.63 |  |  |
| C11 | Plumbing & Drainage |  |  | 1.00 | 215,458 sf | $8.15 | $1,755,000 | $8.15 |  |  |
| C12 | Fire Protection |  |  | 1.00 | 215,458 sf | $5.02 | $1,081,000 | $5.02 |  |  |
| C13 | H.V.A.C. |  |  | 1.00 | 215,458 sf | $39.96 | $8,610,000 | $39.96 | $12,848,000 | 11% |
| C14 | Controls |  |  | 1.00 | 215,458 sf | $6.51 | $1,402,000 | $6.51 |  |  |
| C2 ELECTRICAL |  |  |  |  |  |  |  | $44.26 |  |  |
| C21 | Service & Distribution |  |  | 1.00 | 215,458 sf | $18.00 | $3,878,000 | $18.00 |  |  |
| C22 | Lighting, Devices & Heating |  |  | 1.00 | 215,458 sf | $17.76 | $3,827,000 | $17.76 | $9,536,000 | 8% |
| C23 | Systems & Ancillaries |  |  | 1.00 | 215,458 sf | $8.50 | $1,831,000 | $8.50 |  |  |
| NET BUILDING COST (Excluding Site) |  |  |  |  |  |  |  | $339.72 | $73,195,000 | 62% |
| D SITE & ANCILLARY WORK |  |  |  |  |  |  |  |  |  |  |
| D1 SITE WORK |  |  |  |  |  |  |  | $11.96 |  |  |
| D11 Site Development |  |  |  | 0.05 | 11,809 sf | $150.48 | $1,777,000 | $8.25 |  |  |
| D12 Mechanical Site Services |  |  |  | 0.05 | 11,809 sf | $38.11 | $450,000 | $2.09 | $2,577,000 | 2% |
| D13 Electrical Site Services |  |  |  | 0.05 | 11,809 sf | $29.64 | $350,000 | $1.62 |  |  |
| D2 ANCILLARY WORK |  |  |  |  |  |  |  | $0.00 |  |  |
| D21 Demolition |  |  |  | 0.00 | 0 sf | $0.00 | $0 | $0.00 | $0 | 0% |
| D22 Alterations |  |  |  | 0.00 | 0 sf | $0.00 | $0 | $0.00 |  |  |
| NET BUILDING COST (Including Site) |  |  |  |  |  |  |  | $351.68 | $75,772,000 |  |
| Z GENERAL REQUIREMENTS & ALLOWANCES |  |  |  |  |  |  |  |  |  |  |
| Z1 GEN. REQ. & FEE |  |  | 12.0% |  |  |  |  | $42.20 |  |  |
| Z11 | General Requirements |  | 9.0% |  |  |  | $6,819,000 | $31.65 | $9,092,000 | 8% |
| Z12 | Fee |  | 3.0% |  |  |  | $2,273,000 | $10.55 |  |  |
| TOTAL CONSTRUCTION ESTIMATE (Excluding Allowances) |  |  |  |  |  |  |  |  | $84,864,000 | 71% |
| Z2 ALLOWANCES |  |  | 40.0% |  |  |  |  | $157.54 |  |  |
| Z21 | Estimating Allowance |  | 20.0% |  |  |  | $16,973,000 | $78.78 |  |  |
| Z22 | Escalation Allowance |  | 10.0% 3Q 2019 |  |  |  | $8,485,000 | $39.38 | $33,944,000 | 29% |
| Z23 | Construction Allowance |  | 10.0% |  |  |  | $8,486,000 | $39.39 |  |  |
| TOTAL CONSTRUCTION ESTIMATE (Including Allowances) |  |  |  |  |  |  |  |  | $118,808,000 | 100% |
|  |  |  |  |  |  |  |  |  | Cost/unit |  |
| GFA |  | 215,458 sf |  |  |  |  |  |  | $551 | sf |
| GFA |  | 20,017 m2 |  |  |  |  |  |  | $5,935 | m2 |

18 of 29

|  | OTTAWA PUBLIC LIBRARY (OPL/LAC) - Exemplar Site (Site 8) - Above Grade |  |  |  | File: SS-DD-R9 |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Location: Ottawa, Ontario |  |  |  | Date: Nov 21, 2016 |  |
|  | Owner/Client: City of Ottawa |  |  |  | Project Number: 20940 |  |
|  | Architect: Ajon Moryiama |  | Gross Floor Area: |  |  | 21,548m2 |
|  | Description |  | Quantity |  | Rate | Amount |
|  | GROSS FLOOR AREA |  |  |  |  |  |
|  | TOTAL GROSS FLOOR AREA |  | 71,532 sf |  |  |  |
|  |  |  | 71,532 sf |  |  |  |
|  | A1 SUBSTRUCTURE |  |  |  |  |  |
|  | A11 Foundations |  |  |  |  |  |
|  | OPL |  | 99,211 sf |  | 5.47 | 542,980 |
|  | LAC |  | 54,774 sf |  | 5.47 | 299,780 |
|  | Shared - OPL |  | 33,571 sf |  | 5.47 | 183,730 |
|  | Shared - LAC |  | 27,902 sf |  | 5.47 | 152,710 |
|  | TOTAL A11 Foundations |  | 24,156 sf |  | 48.81 | 1,179,000 |
|  | A12 Basement Excavation |  |  |  |  |  |
|  | OPL |  | 99,211 sf |  | 2.55 | 253,060 |
|  | LAC |  | 54,774 sf |  | 2.55 | 139,720 |
|  | Shared - OPL |  | 33,571 sf |  | 2.55 | 85,630 |
|  | Shared - LAC |  | 27,902 sf |  | 2.55 | 71,170 |
|  | TOTAL A12 Basement Excavation |  | 46,498 cy |  | 11.83 | 550,000 |
|  | TOTAL A1 SUBSTRUCTURE |  |  |  |  |  |
|  |  |  |  |  |  | 1,729,000 |
|  | A2 STRUCTURE |  |  |  |  |  |
|  | A21 Lowest Floor Construction |  |  |  |  |  |
|  | Shared - OPL |  | 33,571 sf |  | 4.52 | 151,710 |
|  | Shared - LAC |  | 27,902 sf |  | 4.52 | 126,100 |
|  | Lowest floor - shared | + | 24,156 sf |  |  |  |
|  | TOTAL A21 Lowest Floor Construction |  | 24,156 sf |  | 11.51 | 278,000 |
|  | A22 Upper Floor Construction |  |  |  |  |  |
|  | Below grade parking - not required |  | 71,532 sf |  |  |  |
|  | OPL |  | 99,211 sf |  | 47.18 | 4,680,670 |
|  | LAC |  | 54,774 sf |  | 47.18 | 2,584,180 |
|  | Shared - OPL |  | 33,571 sf |  | 47.18 | 1,583,840 |
|  | Shared - LAC |  | 27,902 sf |  | 47.18 | 1,316,390 |
|  |  | + | 191,302 sf |  |  |  |
|  | TOTAL A22 Upper Floor Construction |  | 191,302 sf |  | 53.14 | 10,165,000 |
|  | A23 Roof Construction |  |  |  |  |  |
|  | OPL |  | 99,211 sf |  | 14.35 | 1,423,460 |
|  | LAC |  | 54,774 sf |  | 14.35 | 785,890 |
|  | Shared - OPL |  | 33,571 sf |  | 14.35 | 481,670 |
|  | Shared - LAC |  | 27,902 sf |  | 14.35 | 400,330 |
|  | TOTAL A23 Roof Construction |  | 61,827 sf |  | 49.99 | 3,091,000 |
|  | TOTAL A2 STRUCTURE |  |  |  |  |  |
|  |  |  |  |  |  | 13,534,000 |
|  | A3 EXTERIOR ENCLOSURE |  |  |  |  |  |

19 of 29

| OTTAWA PUBLIC LIBRARY (OPL/LAC) - Exemplar Site (Site 8) - Above Grade |  | File: SS-DD-R9 |  |
| --- | --- | --- | --- |
| Location: Ottawa, Ontario |  | Date: Nov 21, 2016 |  |
| Owner/Client: City of Ottawa |  | Project Number: 20940 |  |
| Architect: Ajon Moryiama | Gross Floor Area: |  | 21,548m2 |
| Description | Quantity | Rate | Amount |
| A31 Walls Below Grade |  |  |  |
| OPL | 99,211 sf | 1.07 | 106,320 |
| LAC | 54,774 sf | 1.07 | 58,700 |
| Shared - OPL | 33,571 sf | 1.07 | 35,980 |
| Shared - LAC | 27,902 sf | 1.07 | 29,900 |

20 of 29

|  | OTTAWA PUBLIC LIBRARY (OPL/LAC) - Exemplar Site (Site 8) - Above Grade |  |  | File: SS-DD-R9 |  |
| --- | --- | --- | --- | --- | --- |
|  | Location: Ottawa, Ontario |  |  | Date: Nov 21, 2016 |  |
|  | Owner/Client: City of Ottawa |  |  | Project Number: 20940 |  |
|  | Architect: Ajon Moryiama |  | Gross Floor Area: |  | 21,548m2 |
|  | Description |  | Quantity | Rate | Amount |
|  | TOTAL A31 Walls Below Grade |  | 18,292 sf | 12.63 | 231,000 |
|  | A32 Walls Above Grade |  |  |  |  |
|  | OPL |  | 99,211 sf | 11.78 | 1,168,650 |
|  | LAC |  | 54,774 sf | 11.78 | 645,210 |
|  | Shared - OPL |  | 33,571 sf | 11.78 | 395,450 |
|  | Shared - LAC |  | 27,902 sf | 11.78 | 328,670 |
|  | TOTAL A32 Walls Above Grade |  | 42,300 sf | 60.00 | 2,538,000 |
|  | A33 Windows & Entrances |  |  |  |  |
|  | OPL |  | 99,211 sf | 19.15 | 1,899,600 |
|  | LAC |  | 54,774 sf | 19.15 | 1,048,760 |
|  | Shared - OPL |  | 33,571 sf | 19.15 | 642,790 |
|  | Shared - LAC |  | 27,902 sf | 19.15 | 534,240 |
|  | TOTAL A33 Windows & Entrances |  | 26,392 sf | 156.30 | 4,125,000 |
|  | A34 Roof Covering |  |  |  |  |
|  | OPL |  | 99,211 sf | 11.70 | 1,160,530 |
|  | LAC |  | 54,774 sf | 11.70 | 640,720 |
|  | Shared - OPL |  | 33,571 sf | 33.08 | 1,110,590 |
|  | Shared - LAC |  | 27,902 sf | 33.08 | 923,040 |
|  | TOTAL A34 Roof Covering |  | 61,827 sf | 62.03 | 3,835,000 |
|  | A35 Projections |  |  |  |  |
|  | OPL | + | 99,211 sf | 3.47 | 344,090 |
|  | LAC | + | 54,774 sf | 3.47 | 189,970 |
|  | Shared - OPL | + | 33,571 sf | 3.47 | 116,430 |
|  | Shared - LAC | + | 27,902 sf | 3.47 | 96,770 |
|  | TOTAL A35 Projections |  | 215,458 sf | 3.47 | 747,000 |
|  | TOTAL A3 EXTERIOR ENCLOSURE |  |  |  |  |
|  |  |  |  |  | 11,476,000 |
|  | TOTAL A SHELL |  |  |  |  |
|  |  |  |  |  | 26,739,000 |
|  | B1 PARTITIONS & DOORS |  |  |  |  |
|  | B11 Partitions |  |  |  |  |
|  | OPL |  | 99,211 sf | 25.48 | 2,527,970 |
|  | LAC |  | 54,774 sf | 25.48 | 1,395,680 |
|  | Shared - OPL |  | 33,571 sf | 20.78 | 697,620 |
|  | Shared - LAC |  | 27,902 sf | 20.78 | 579,820 |
|  | TOTAL B11 Partitions |  | 174,521 sf | 29.80 | 5,201,000 |
|  | B12 Doors |  |  |  |  |

21 of 29

|  | OTTAWA PUBLIC LIBRARY (OPL/LAC) - Exemplar Site (Site 8) - Above Grade |  | File: SS-DD-R9 |  |
| --- | --- | --- | --- | --- |
|  | Location: Ottawa, Ontario |  | Date: Nov 21, 2016 |  |
|  | Owner/Client: City of Ottawa |  | Project Number: 20940 |  |
|  | Architect: Ajon Moryiama | Gross Floor Area: |  | 21,548m2 |
|  | Description | Quantity | Rate | Amount |
|  | OPL | 99,211 sf | 4.12 | 409,180 |
|  | LAC | 54,774 sf | 4.12 | 225,910 |
|  | Shared - OPL | 33,571 sf | 2.70 | 90,580 |
|  | Shared - LAC | 27,902 sf | 2.70 | 75,290 |
|  | TOTAL B12 Doors | 400 No | 2000.10 | 801,000 |
|  | TOTAL B1 PARTITIONS & DOORS |  |  |  |
|  |  |  |  | 6,002,000 |
|  | B2 FINISHES |  |  |  |
|  | B21 Floor Finishes |  |  |  |
|  | OPL | 99,211 sf | 21.00 | 2,083,440 |
|  | LAC | 54,774 sf | 21.00 | 1,150,260 |
|  | Shared - OPL | 33,571 sf | 13.50 | 453,210 |
|  | Shared - LAC | 27,902 sf | 13.50 | 376,680 |
|  | TOTAL B21 Floor Finishes | 215,458 sf | 18.86 | 4,064,000 |
|  | B22 Ceiling Finishes |  |  |  |
|  | OPL | 99,211 sf | 14.99 | 1,487,410 |
|  | LAC | 54,774 sf | 14.99 | 821,190 |
|  | Shared - OPL | 33,571 sf | 14.99 | 503,310 |
|  | Shared - LAC | 27,902 sf | 14.99 | 418,320 |
|  | TOTAL B22 Ceiling Finishes | 215,458 sf | 14.99 | 3,230,000 |
|  | B23 Wall Finishes |  |  |  |
|  | OPL | 99,211 sf | 11.71 | 1,162,170 |
|  | LAC | 54,774 sf | 11.71 | 641,630 |
|  | Shared - OPL | 33,571 sf | 11.71 | 393,250 |
|  | Shared - LAC | 27,902 sf | 11.71 | 326,850 |
|  | TOTAL B23 Wall Finishes | 563,455 sf | 4.48 | 2,524,000 |
|  | TOTAL B2 FINISHES |  |  |  |
|  |  |  |  | 9,818,000 |
|  | B3 FITTINGS & EQUIPMENT |  |  |  |
|  | B31 Fittings & Fixtures |  |  |  |
|  | OPL | 99,211 sf | 24.93 | 2,473,030 |
|  | LAC | 54,774 sf | 27.55 | 1,509,230 |
|  | Shared - OPL | 33,571 sf | 24.93 | 836,820 |
|  | Shared - LAC | 27,902 sf | 27.55 | 913,110 |
|  | TOTAL B31 Fittings & Fixtures | 215,458 sf | 26.60 | 5,732,000 |
|  | B32 Equipment |  |  |  |
|  | Retractable seating | 250 no | 1000.00 | 250,000 |
|  | Allowance for stage - excluded |  |  |  |

22 of 29

|  | OTTAWA PUBLIC LIBRARY (OPL/LAC) - Exemplar Site (Site 8) - Above Grade |  |  | File: SS-DD-R9 |  |
| --- | --- | --- | --- | --- | --- |
|  | Location: Ottawa, Ontario |  |  | Date: Nov 21, 2016 |  |
|  | Owner/Client: City of Ottawa |  |  | Project Number: 20940 |  |
|  | Architect: Ajon Moryiama |  | Gross Floor Area: |  | 21,548m2 |
|  | Description |  | Quantity | Rate | Amount |
|  | TOTAL B32 Equipment |  | 215,458 sf | 1.16 | 250,000 |
|  | B33 Conveying Systems |  |  |  |  |
|  | OPL |  | 99,211 sf | 10.54 | 1,045,260 |
|  | LAC |  | 54,774 sf | 10.54 | 577,080 |
|  | Shared - OPL |  | 33,571 sf | 10.54 | 353,690 |
|  | Shared - LAC |  | 27,902 sf | 10.54 | 293,970 |
|  | TOTAL B33 Conveying Systems |  | 48 Stp | 47291.67 | 2,270,000 |
|  | TOTAL B3 FITTINGS & EQUIPMENT |  |  |  |  |
|  |  |  |  |  | 8,252,000 |
|  | TOTAL B INTERIORS |  |  |  |  |
|  |  |  |  |  | 24,072,000 |
|  | C1 MECHANICAL |  |  |  |  |
|  | C11 Plumbing & Drainage |  |  |  |  |
|  | Allowance | + | 215,458 sf |  |  |
|  | OPL |  | 99,211 sf | 10.00 | 992,110 |
|  | LAC |  | 54,774 sf | 10.00 | 547,740 |
|  | Shared - OPL |  | 33,571 sf | 3.50 | 117,500 |
|  | Shared - LAC |  | 27,902 sf | 3.50 | 97,660 |
|  | TOTAL C11 Plumbing & Drainage |  | 215,458 sf | 8.15 | 1,755,000 |
|  | C12 Fire Protection |  |  |  |  |
|  | Allowance |  |  |  |  |
|  | OPL | + | 99,211 sf | 4.00 | 396,840 |
|  | LAC | + | 54,774 sf | 8.00 | 438,190 |
|  | Shared - OPL | + | 33,571 sf | 4.00 | 134,280 |
|  | Shared - LAC | + | 27,902 sf | 4.00 | 111,610 |
|  | TOTAL C12 Fire Protection |  | 215,458 sf | 5.02 | 1,081,000 |
|  | C13 HVAC |  |  |  |  |
|  | Allowance |  |  |  |  |
|  | OPL | + | 99,211 sf | 40.00 | 3,968,440 |
|  | LAC | + | 54,774 sf | 40.00 | 2,190,960 |
|  | Shared - OPL | + | 21,612 sf | 35.00 | 756,430 |
|  | Atrium area - smoke vac allowance | + | 11,959 sf | 60.00 | 717,530 |
|  | Shared - LAC | + | 27,902 sf | 35.00 | 976,570 |
|  | TOTAL C13 HVAC |  | 215,458 sf | 39.96 | 8,610,000 |
|  | C14 Controls |  |  |  |  |
|  | Allowance |  |  |  |  |
|  | OPL | + | 99,211 sf | 6.00 | 595,270 |
|  | LAC | + | 54,774 sf | 8.00 | 438,190 |
|  | Shared - OPL | + | 33,571 sf | 6.00 | 201,430 |
|  | Shared - LAC | + | 27,902 sf | 6.00 | 167,410 |

23 of 29

|  | OTTAWA PUBLIC LIBRARY (OPL/LAC) - Exemplar Site (Site 8) - Above Grade |  |  | File: SS-DD-R9 |  |
| --- | --- | --- | --- | --- | --- |
|  | Location: Ottawa, Ontario |  |  | Date: Nov 21, 2016 |  |
|  | Owner/Client: City of Ottawa |  |  | Project Number: 20940 |  |
|  | Architect: Ajon Moryiama |  | Gross Floor Area: |  | 21,548m2 |
|  | Description |  | Quantity | Rate | Amount |
|  | TOTAL C14 Controls |  | 215,458 sf | 6.51 | 1,402,000 |
|  | TOTAL C1 MECHANICAL |  |  |  |  |
|  |  |  |  |  | 12,848,000 |
|  | C2 ELECTRICAL |  |  |  |  |
|  | C21 Service & Distribution |  |  |  |  |
|  | Allowance |  |  |  |  |
|  | OPL | + | 99,211 sf | 18.00 | 1,785,800 |
|  | LAC | + | 54,774 sf | 18.00 | 985,930 |
|  | Shared - OPL | + | 33,571 sf | 18.00 | 604,280 |
|  | Shared - LAC | + | 27,902 sf | 18.00 | 502,240 |
|  | TOTAL C21 Service & Distribution |  | 215,458 sf | 18.00 | 3,878,000 |
|  | C22 Lighting, Devices & Heating |  |  |  |  |
|  | Allowance |  |  |  |  |
|  | OPL | + | 99,211 sf | 17.00 | 1,686,590 |
|  | LAC | + | 54,774 sf | 20.00 | 1,095,480 |
|  | Shared - OPL | + | 33,571 sf | 17.00 | 570,710 |
|  | Shared - LAC | + | 27,902 sf | 17.00 | 474,330 |
|  | TOTAL C22 Lighting, Devices & Heating |  | 215,458 sf | 17.76 | 3,827,000 |
|  | C23 Systems & Ancillaries |  |  |  |  |
|  | Allowance |  |  |  |  |
|  | OPL | + | 99,211 sf | 8.50 | 843,290 |
|  | LAC | + | 54,774 sf | 8.50 | 465,580 |
|  | Shared - OPL | + | 33,571 sf | 8.50 | 285,350 |
|  | Shared - LAC | + | 27,902 sf | 8.50 | 237,170 |
|  | TOTAL C23 Systems & Ancillaries |  | 215,458 sf | 8.50 | 1,831,000 |
|  | TOTAL C2 ELECTRICAL |  |  |  |  |
|  |  |  |  |  | 9,536,000 |
|  | TOTAL C SERVICES |  |  |  |  |
|  |  |  |  |  | 22,384,000 |
|  | NET BUILDING COST (EXCLUDING SITE) |  |  |  |  |
|  |  |  |  |  | 73,195,000 |
|  | D1 SITE WORK |  |  |  |  |
|  | D11 Site Development |  |  |  |  |
|  | OPL |  | 99,211 sf | 8.25 | 818,310 |
|  | LAC |  | 54,774 sf | 8.25 | 451,790 |
|  | Shared - OPL |  | 33,571 sf | 8.25 | 276,900 |
|  | Shared - LAC |  | 27,902 sf | 8.25 | 230,140 |
|  | TOTAL D11 Site Development |  | 11,809 sf | 150.48 | 1,777,000 |
|  | D12 Mechanical Site Services |  |  |  |  |
|  | OPL |  | 99,211 sf | 2.09 | 207,210 |
|  | LAC |  | 54,774 sf | 2.09 | 114,400 |
|  | Shared - OPL |  | 33,571 sf | 2.09 | 70,120 |
|  | Shared - LAC |  | 27,902 sf | 2.09 | 58,280 |

24 of 29

|  | OTTAWA PUBLIC LIBRARY (OPL/LAC) - Exemplar Site (Site 8) - Above Grade |  |  | File: SS-DD-R9 |  |
| --- | --- | --- | --- | --- | --- |
|  | Location: Ottawa, Ontario |  |  | Date: Nov 21, 2016 |  |
|  | Owner/Client: City of Ottawa |  |  | Project Number: 20940 |  |
|  | Architect: Ajon Moryiama |  | Gross Floor Area: |  | 21,548m2 |
|  | Description |  | Quantity | Rate | Amount |
|  | TOTAL D12 Mechanical Site Services |  | 11,809 sf | 38.11 | 450,000 |
|  | D13 Electrical Site Services |  |  |  |  |
|  | OPL |  | 99,211 sf | 1.62 | 161,160 |
|  | LAC |  | 54,774 sf | 1.62 | 88,980 |
|  | Shared - OPL |  | 33,571 sf | 1.62 | 54,530 |
|  | Shared - LAC |  | 27,902 sf | 1.62 | 45,330 |
|  | TOTAL D13 Electrical Site Services |  | 11,809 sf | 29.64 | 350,000 |
|  | TOTAL D1 SITE WORK |  |  |  |  |
|  |  |  |  |  | 2,577,000 |
|  | D2 ANCILLARY WORK |  |  |  |  |
|  | D21 Demolition |  |  |  |  |
|  | TOTAL D21 Demolition |  | sf | 0.00 | 0 |
|  | D22 Alterations |  |  |  |  |
|  | N/A |  |  |  |  |
|  | TOTAL D22 Alterations |  | 0 sf | 0.00 | 0 |
|  | TOTAL D2 ANCILLARY WORK |  |  |  |  |
|  |  |  |  |  | 0 |
|  | TOTAL D SITE & ANCILLARY WORK |  |  |  |  |
|  |  |  |  |  | 2,577,000 |
|  | NET BUILDING COST (INCLUDING SITE) |  |  |  |  |
|  |  |  |  |  | 75,772,000 |
|  | Z1 GENERAL REQUIREMENTS & FEE |  |  |  |  |
|  | Z11 General Requirements |  |  |  |  |
|  | General Requirements |  | ls |  | 6,819,000 |
|  | TOTAL Z11 General Requirements |  |  |  | 6,819,000 |
|  | Z12 Fee |  |  |  |  |
|  | Fee |  | ls |  | 2,273,000 |
|  | TOTAL Z12 Fee |  |  |  | 2,273,000 |
|  | TOTAL Z1 GENERAL REQUIREMENTS & FEE |  |  |  |  |
|  |  |  |  |  | 9,092,000 |
|  | TOTAL CONSTRUCTION ESTIMATE EXCLUDING ALLOWANCES |  |  |  |  |
|  |  |  |  |  | 84,864,000 |
|  | Z2 CONTINGENCIES |  |  |  |  |

25 of 29

|  | OTTAWA PUBLIC LIBRARY (OPL/LAC) - Exemplar Site (Site 8) - Above Grade |  | File: SS-DD-R9 |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Location: Ottawa, Ontario |  | Date: Nov 21, 2016 |  |  |
|  | Owner/Client: City of Ottawa |  | Project Number: 20940 |  |  |
| Architect: Ajon Moryiama |  | Gross Floor Area: |  | 21,548m2 |  |
| Description |  | Quantity | Rate | Amount |  |
| Z21 Estimating Contingency |  |  |  |  |  |
| Estimating Contingency |  | ls |  | 16,973,000 |  |
| TOTAL Z21 Estimating Contingency |  |  |  | 16,973,000 |  |
| Z22 Escalation Contingency |  |  |  |  |  |
| Escalation Contingency |  | ls |  | 8,485,000 |  |
| TOTAL Z22 Escalation Contingency |  |  |  | 8,485,000 |  |
| Z23 Construction Contingency |  |  |  |  |  |
| Construction Contingency |  | ls |  | 8,486,000 |  |
| Total Z23 Construction Contingency |  |  |  | 8,486,000 |  |
| TOTAL Z2 CONTINGENCIES |  |  |  |  |  |
|  |  |  |  | 33,944,000 |  |
| TOTAL Z GENERAL REQUIREMENTS & CONTINGENCIES |  |  |  |  |  |
|  |  |  |  | 43,036,000 |  |
| TOTAL BUILDING COST INCLUDING ALLOWANCES |  |  |  |  |  |
|  |  |  |  | 118,808,000 |  |

26 of 29

Ottawa Public Library (OPL/LAC), Exemplar Site (Site 8)

City of Ottawa

- AREA SUMMARY

27 of 29

Ottawa Library and LAC For Exemplar Site (Site 8)

Class D

City of Ottawa

|  | Revision: |  | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | Area Schedule |  |  |  |  |  |  |  |  |  |  |  |
|  |  | PARKING |  | Shared - OPL | Shared - LAC |  |  |  |  |  |  |  |  |  |  |  |  | GROSS |  |
|  | FLOOR |  |  |  |  | OPL | LAC |  |  |  |  |  |  |  |  |  |  | INTERNAL |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | FLOOR |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | AREA |  |
|  | Level 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0 |  |
|  | Level 1 | 71,532 |  | 33,571 | 27,902 | 99,211 | 54,774 |  |  |  |  |  |  |  |  |  |  | 286,990 |  |
|  | Level 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0 |  |
|  | Level 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0 |  |
|  | Level 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0 |  |
|  | TOTAL | 71,532 |  | 33,571 | 27,902 | 99,211 | 54,774 |  |  |  |  |  |  |  |  |  |  | 286,990 |  |
|  | Last Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Movement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Area Schedule |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | making the difference |  |  |

28 of 29

Ottawa Library and LAC For Exemplar Site (Site 8)

City of Ottawa

4 DOCUMENT LIST

| Dwg no. |  |  |  |  |  |  |  |  |  |  |  | Document | Prepared By | Dated | Date Received |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | ARCHITECTURAL |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Updated sketches |  |  |  |  |  |  |  |  |  |  |  | Ajon Moryiama | 21/6/2016 | 25-Oct-2016 |
|  | Updated GFA |  |  |  |  |  |  |  |  |  |  |  | OPL | 2-Nov-2016 | 2-Nov-2016 |
|  |  | STRUCTURAL |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | N/A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | LANDSCAPE |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | N/A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | CIVILS |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | N/A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | MECHANICAL |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | N/A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | ELECTRICAL |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | N/A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | SPECIFICATIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | N/A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

29 of 29